## Project Planner
Date Randomizer
[5 empty] | Period Highlight: | 18 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | April
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Interview Business Manager | 18 | 1 | 18 | 1 | 100%
Generate User Stories | 19 | 2 | 19 | 2 | 50%
Extract system requirements | 19 | 2 | 19 | 2 | 25%
Build use cases/DFD/Context Diagram | 20 | 2 | 20 | 2 | 0%
Setup Android Studio on PC | 21 | 1 | 21 | 1 | 0%
Obtain Google Maps API Key | 21 | 1 | 21 | 1 | 0%
Go over google maps API documentation | 22 | 2 | 22 | 2 | 0%
Build user interface in android studio | 23 | 1 | 23 | 1 | 0%
Setup multiple fragments/textviews/buttons/etc. in AS | 23 | 2 | 23 | 2 | 0%
Design Login System(should communicate through main activity) | 24 | 4 | 24 | 4 | 0%
Create Github repo | 24 | 1 | 24 | 1 | 0%
Using google maps, generate random itinerary | 24 | 4 | 24 | 4 | 0%
Final output/demo video | 25 | 1 | 25 | 1 | 0%